## Sheet1
BA Hours
BA Tracked | Task | Responsible | Consulted / Contributor | Informed | Est Best | Est Expected | Est Worst | Actual | Planned Activities
| Opportunity Checkpoint (Enterprise Analysis) | [7 empty] | x
| Complete the Opportunity Profile Template | BP | BA |  | 3 | 6 | 10
| Complete Gap 'As Is' Analysis (High level) | BP | BA |  | 3 | 5 | 5
| Complete Gap 'To Be' Analysis (Initial, High level) | BP | BA |  | 4 | 6 | 7
| Develop Benefit Realization Model (BRM) | BA | PM, BP
| Validate Benefit Realization Model | BA | PM, BP
x | Total |  |  |  | 10 | 17 | 22 | 0 | x
x | Scope Checkpoint (Enterprise Analysis and Business Analysis Planning) | [7 empty] | x
x | Project Scope (Charter) | PM | BA |  | 5 | 8 | 20 |  | x
| Document the Business Problem Statement section | BA | PM
| Document the Business Case section | BA | PM
| Review Objectives/Deliverables section | PM | BA
| Review Critical Success Factors section | PM | BA
| Review Risk, Constraints, Dependencies, etc. section | PM | BA
| Document the Costs/Benefits section | PM | BA. BP
| Review the Estimation (Resources & Time) section | PM | BA
x | High Level Requirements | BA | PM, BP | [5 empty] | x
x | Execute Stakeholder Analysis | BA | PM, BP |  | 3 | 5 | 7 |  | x
| Develop BA Activity Plan | BA | PM
| Requirements Management Plan | BA
| Develop a Requirements Gathering Plan | BA | PM |  | 1 | 2 | 3
| Develop BA Requirements Communication Plan | BA | PM
| Document Risks, Constraints, Dependencies, etc. | BA | PM
| Determine which process flows/diagrams to develop | BA | PM, BP, TL
x | Document necessary process flow & diagrams | BA | [6 empty] | x
x | Context Diagram | BA |  |  | 2 |  |  |  | x
x | Document the End-to-End Process Flow (swimlane) - per Level 2 process | BA |  |  | 2 |  |  |  | x
x | Use Case Diagram - per level 2 process per environment | BA |  |  | 4 |  |  |  | x
| Class Diagram - per level 2 process | BA |  |  | 2
| Deployment diagram | TL | BA |  | 1
| List of As-Is Requirements Artifacts | BA
List of To-Be Requirements Artifacts
| Establish a Knowledge Management Plan | BA |  |  | 1 | 1 | 2
| Review Project Plan with PM | BA |  |  | 1 | 1 | 2
| Update Risks, Constraints, Dependencies, etc. | PM | BA |  | 1 | 2 | 4
x | Total |  |  |  | 23 | 19 | 38 | 0 | x
x | Interlock Checkpoint (Requirements Elicitation, Analysis, Management, Communication) | [7 empty] | x
x | Create Requirements Package (Possible components listed below) | BA | PM, TL | [5 empty] | x
x | Document Use Cases | BA | [6 empty] | x
| Add Use Case references to Scope Matrix | BA
| Create a Functional Decomposition | BA |  |  | 4 | 5 | 8
| Prototypes | BA |  |  | 2 | 4 | 7
| UML Diagrams / Sequence Diagrams | BA |  |  | 3 | 6 | 13
| DataFlow Diagram | BA |  |  | 1 | 2 | 5
| Entity Relation Diagram | TL |  |  | 3 | 6 | 12
x | Create and manage a Traceability Matrix (deliverable for Execute Checkpoint) | BA |  |  | 1 | 1 | 1 |  | x
| List out Non-functional Requirements | BA | PM, TL |  | 1 | 1 | 2
| Peer Review of Requirements Package | PM |  |  | 1 | 1 | 2
| Communicate and obtain Sign off for Requirements Package | PM |  |  | 1 | 1 | 2
| Set up Meeting with Stakeholders | PM
| Review Business Requirements Document | BA
| Review Requirement Priority | BA
| Obtain approvals for Milestone Checkpoints (Business, Finance, Compliance) | PM |  |  | 1 | 1 | 1
| Review Project Plan with PM | PM | BA, BP |  | 1 | 1 | 1
x | Total |  |  |  | 19 | 29 | 54 | 0 | x
x | Design Review (Requirements Analysis, Solution Assessment, and Solution Validation) | [7 empty] | x
| Review Functional and Technical Design Specs | TL | BA |  | 1 | 2 | 3
| Review Architecture/Design | TL | BA |  | 1 | 2 | 3
| Update Traceability Matrix | BA |  |  | 1 | 1 | 1
| Update Diagrams and flows as needed | BA |  |  | 1 | 1 | 1
x | Create UAT Test Plan | BA |  |  | 0.5 | 0.5 | 1 |  | x
| Identify UAT testers | BA,PM
| Establish UAT Objectives and Success Criteria | BA
x | Create UAT Test Cases | BA | [6 empty] | x
| Create UAT Test Runs | BA
| Review QA Test Plan | BA
| Review Project Plan with PM | BA |  |  | 1 | 1 | 1
| Status Review with IT (on Unit and System Testing) | PM |  |  | 0.5 | 0.5 | 0.5
| Review Test Results | BA |  |  | 0.5 | 0.5 | 1
x | Total |  |  |  | 6.5 |  |  |  | x
x | Execute Checkpoint (User Acceptance, Solution Assessment and Test Plan) | [7 empty] | x
| Verify migration and setup in UAT Instance (Stage) | BA |  |  | 0.5 | 0.5 | 0.5
| Freeze the UAT instance (Stage) | TL |  |  | 0 | 0 | 0
| UAT Kickoff and Coordination | BA
| UAT Status Review with PM | BA |  |  | 0 | 0 | 0
| Log Bugs and Resolution Tracking | BA |  |  | 0.5 | 0.5 | 1
| Assign Bug Priority | BA |  |  | 0.5 | 0.5 | 1
| Determine lessons learned in testing | BA |  |  | 0.5 | 0.5 | 1
| Log Root Cause Analysis (Criticals and Majors) from IT | BA |  |  | 0.5 | 0.5 | 0.5
| Review Success Criteria / Determine Escalation Items | BA |  |  | 0 | 0 | 0
| Review Bug Fixes | BA |  |  | 1 | 1 | 2
x | Execute UAT and obtain signoff from stakeholders | BA | [6 empty] | x
| Review UAT Results | PM | BA |  | 0.5 | 0.5 | 0.5
| Create and provide Training Docs and Help Desk Setup | BA |  |  | 3 | 5 | 8
| Provide Training to Support Team / Business Team | BA |  |  | 3 | 5 | 10
| Coordinate Go-No-Go Meeting with Stakeholders and PM | PM |  |  | 0 | 0 | 0
| Review Change Management Documents | PM | BA |  | 0 | 0 | 0
| Review Deployment Checklist / Playbook | PM, TL | BA |  | 0 | 0 | 0
x | Total | [7 empty] | x
x | Close Checkpoint (Project Wrap Up) | [7 empty] | x
| Post Deployment - Gather User Feedback | BA |  |  | 1 | 1.5 | 2
| Post Deployment - Identify Improvement Areas | BA |  |  | 0.5 | 0.5 | 0.5
| Outstanding Issues and Next Phase | PM |  |  | 2 | 4 | 8
| Share Root Cause Analysis for Issues | BA |  |  | 0 | 0 | 0
| Complete Change Management Processes | PM |  |  | 0.5 | 0.5 | 0.5
x | Archive final versions of BA deliverables | BA | [6 empty] | x
x | Total | [7 empty] | x
x | General (throughout Project) | [7 empty] | x
| Document Meeting Minutes | BA |  |  | 5 | 7 | 10
| Facilitate Requirements Change Management Process | PM | BA |  | 1 | 2 | 4
x | Total | [7 empty] | x